## Sheet1
INITIAL PLAN- Treasure Hunt
Start Date | 2011-01-17
Finish Date
Main task | Sub task | Time
scenario | read through SPB | 30
Planning | Create initial plan | 60
| agree with teacher | 5
keeping track | create ongoing plan | 5
| set up project log | 25
Overview | read what is needed for each component | 10
Gathering Assets | Create Assets table | 10
| Save your assets table | 5
Proposal | read instructions | 30
| fill out proposal | 5
| check with teacher | 15
The Tasks Task 1: | Produce a Story board for the Puzzles | 120
| Get feedback from test users | 15
| Make the puzzles | 240
| Get feedback from test users | 15
Task 2: | Design the Animation | 120
| Get feedback from test users | 10
| Produce the animation | 180
| Get feedback from test users | 10
Task 3: | produce a time line story board | 120
| Get feedback from test users | 10
| Produce and edit movie | 120
| Get feedback from test users | 10
| Updata assets table | 5
The other parts | design your map and save it | 180
| make your map | 180
| ask for feed back if necessary | 5
| updata assets table and ongoing plan | 5
| design and create the instructions screen | 60
| ask for feed back if necessary | 5
| updata ongoing plan | 5
| save the flash movie and text file | 5
| change the numbers to 1234567890 | 5
| link the flash movie to the map | 5
| try to check it works | 10
| updata assets table and ongoing plan | 5
Building it | making sure all components are in the tresure folder | 10
| build the treasure hunt | 180
| test the treasure hunt | 20
| try treasure hunt with the audince | 30
| updata ongoing plan | 10
E-portfolio | create list | 10
| Design Webpage | 240
Review | ask for review on your treasure hunt | 45
| create detailed project review | 180
| Total | 22.20hrs