## Sheet1
On-going plan: Treasure Hunt
Start Date | 2011-04-20
Finish Date
Main task | Sub task | Time | Time taken | Contingency time | Notes
scenario | read through SPB | 30 | 20 | 10 | Not hard to read, however some bits had to be read twice or three times to make sure I understand it fully
Planning | Create initial plan | 60 | 30 | 30 | creating initial plan was a bit difficult as I had not created on by myself before as we were provided with it already, however I believe trying new things is the way forward. Therefore I do not have any negativity.
| agree with teacher | 5 | 5 | 0 | The teacher agreed with my initial plan and also with my ongoing plan. He found it brilliant, there were some aspects which I had to change which I did.
keeping track | create ongoing plan | 5 | 2 | 3 | Was very easy, it took me less then a minute to do the ongoing plan as I had to just copy the initial plan and save this copy as ongoing plan and keep making changes to it. Brilliant!!!
| Set up project log | 25 | 10 | 15 | was quite easy setting up, however I found filling in the column as bit difficult, I think it may be due to the reason that I had not ever done the project logo in much detail in my other projects so it was my first time doing the project log in detail. However I believe I will get used to it
Overview | read what is needed for each component | 10 | 10 | 0 | I had to read the pages few times to understand what was needed for each compenent. It was really easy but there were some treaky words therefore I has to read it a couple of times.
Gathering Assets | Create Assets table | 10 | 5 | 5 | not hard, I had created one before already for previous projects therefore was fimilar with it. So creating this was leass complicated. The assets tabel bacically included all the pictures which I had used throughout the project. This meant primary and secondary sources. i had to write picture discription, where used and if permission was needed if the picture was used. also whether the picture was primary or secondary so taken from internet or made by myself.
| Save your assets table | 5 | 2 | 2
Proposal | read instructions | 30 | 10 | 20
| fill out proposal | 30 | 60 | -30
| check with teacher | 15 | 1 | 14
The Tasks Task 1: | Produce a Story board for the Puzzles | 120
| Get feedback from test users | 15
| Make the puzzles | 240
| Get feedback from test users | 15
Task 2: | Design the Animation | 120
| Get feedback from test users | 10
| Produce the animation | 180
| Get feedback from test users | 10
Task 3: | produce a time line story board | 120
| Get feedback from test users | 10
| Produce and edit movie | 120
| Get feedback from test users | 10
| Update assets table | 5
The other parts | Design your map and save it | 180
| Make your map | 180
| Ask for feed back if necessary | 5
| Update assets table and ongoing plan | 5
| Design and create the instructions screen | 60
| Ask for feed back if necessary | 5
| Update ongoing plan | 5
| Save the flash movie and text file | 5
| Change the numbers to 1234567890 | 5
| Link the flash movie to the map | 5
| Try to check it works | 10
| Update assets table and ongoing plan | 5
Building it | Making sure all components are in the treasure folder | 10
| Build the treasure hunt | 180
| Test the treasure hunt | 20
| Try treasure hunt with the audience | 30
| Update ongoing plan | 10
E-portfolio | Create list | 10 | 10 | 0
| Design Webpage | 240 | 260 | 20
Review | Ask for review on your treasure hunt | 45
| Create detailed project review | 180
| Total | 22.20hrs